## ALL (2)
TRAVEL START DATE |  | 2013-01-10 |  | PROJECT NAME
TRAVEL END DATE |  | 2012-01-31 |  | TRAINED TEAM LEADER
TL= TEAM LEADER LC=LOGISTICS COORD MD=MISSION DIRECTOR MB=MISSION BOOKKEEPER TT=TEAM TREASURER |  |  |  | MISSION DIRECTOR
| TARGET DATE | COMPLETED | PERSON RESPONSIBLE | TASK DESCRIPTION | www.woodstockmissions.com
Required for Project Approval prior to month 6
1 |  |  | TL | Complete Team Leader Training
2 |  |  | MD/TL | Contact field partner to discuss, dates, cost and ministry opportunites for your team (skype)
3 |  |  | TL | Check on visa/immunization requirements and travel warnings http://travel.state.gov/
4 |  |  | MD/TL | Contact Missions Director (MD) for project assessment & training schedule/details
5 |  |  | TL | Submit a completed Proposed Project Fact Sheet to MD for review | Proposed Project Fact Sheet
6 |  |  | TL | Submit a completed Project Budget to MD for review | Budget
7 |  |  | MD | MD will notify you when your project has been approved
8 |  |  | MD | MD send Mission Staff an approval email with Project Fact Sheet
9 |  |  | MD | Finance will assign a Project Account Number beginning with a zero balance
Month 6 prior to departure
10 | 2012-07-10 |  | TL/LC | Meet with MD and Mission's Logistic Coordinator (LC) | Project Checklist
11 | 2012-07-10 |  | TL/LC | Set training schedule and book rooms with LC including informational meeting
12 | 2012-07-10 |  | TL/LC | Request First Focus promotion for informational meeting
13 | 2012-07-10 |  | MD/TL | Pray and fast for God to bring the right team members
Month 5 prior to departure
14 | 2012-08-10 |  | TL | Conduct informational meeting and use project fact sheet (150 days out)
15 | 2012-08-10 |  | TL | Ask all potential team members to visit missions's website to complete the online application | Team Member Application
16 | 2012-08-10 |  | TL | Review applications and select your team (conduct interviews and check references as needed)
17 | 2012-08-10 |  | TL | Turn in copy of team member's signed application, including background check request (for team members over age 18) and the 10% nonrefundable deposit = initial contribution from team member's personal funds to LC
18 | 2012-08-10 |  | TL | Pick up Team Member training materials from LC
120 days prior to departure
19 | 2012-09-10 |  | TL/MD | Team Training Session #1
20 | 2012-09-10 |  | TL/MD | Disciple your team in support discovery/letters
21 | 2012-11-10 |  | TL | Complete Team Travel List and email form to LC (teams aren't put on the online giving website until list is received by LC) | Team Travel LIst
23 | 2012-09-10 |  | TL | Distribute Team Member training materials
24 | 2012-09-10 |  | TL | Select Prayer Captain
25 | 2012-09-10 |  | TL | Select Team Treasurer and notify MB include name and contact info
26 | 2012-09-10 |  | TL | Give team members the Project Account Number and their project code for support letters
27 | 2012-09-10 |  | TL/MD | Request team members to email you their support letter prior to mailing for review
28 | 2012-09-10 |  | TL | Encourage team members to send approximately 100 letters for prayer and financial support
29 | 2012-09-10 |  | TL | Team members begin building a prayer support team | Prayer Support Team Form
30 | 2012-09-10 |  | TT | Coach team members to use the Prayer/Support Team Tracker Spreadsheet | Prayer/Support Tracker
31 | 2012-09-10 |  | TL | Discuss team communication options - phone, email, Facebook group, What's App
32 | 2012-09-10 |  | TL | Take team photo and email it to LC for prayer/thank you cards (printing quality photo please)
90 days prior to departure
33 | 2012-10-10 |  | TL/MD | Team Training Session #2
34 | 2012-10-10 |  | TT | 25% of per person cost is due from each team member
35 | 2012-10-10 |  | TL | Collect Prayer Support Team Worksheet from each team member give to team Prayer Captain | Prayer Support Team
36 | 2012-10-10 |  | TL | Meet with MD & LC to go over Project Checklist
37 | 2012-10-10 |  | TT | Team Treasurer to turn in all money to MB in Mission Envelope provided at Treasurer Training
38 |  |  | TL/LC | Airline quote (Remember, each person needs enough funds to cover the ticket price before purchase date.)
39 | 2012-10-10 |  | TL/MD | Review any support-raising concerns with MD if not at 50% as a team or 50% for an individual
70 days prior to departure
39 | 2012-11-10 |  | TL/MD | Team Training Session #3
40 | 2012-11-10 |  | TT | 50% of per person cost is due from each team member
41 | 2012-11-10 |  | TL | Give LC copies of all passports and health insurance cards
43 | 2012-11-10 |  | TL | Complete Emergency Contact Sheet and Evacuation Plan (check with field partner for assistance) | ER Contact Sheet and Evac Plan
44 | 2012-11-10 |  | TL/MD | Review any support-raising concerns with MD if not at 50% as a team or 50% for an individual
45 | 2012-11-10 |  | TL | Remind your team to use the Team Prayer Cards as Thank You cards for supporters
46 | 2012-11-10 |  | TL | Contact LC to purchase airline tickets
47 | 2012-11-10 |  | LC | LC will book church vans to take your team to and from the airport if available.
48 | 2012-11-10 |  | TL | Please arrange for someone outside your team to drive the vans and give LC their contact info
50 days prior to departure
51 | 2012-12-10 |  | TL/MD | Team Training Session #4
52 | 2012-12-10 |  | TT | 75% of per person cost is due form each team member
53 | 2012-12-10 |  | TL | Prayer Captain to encourage each team member to pray/fast for one day prior to departure
54 | 2012-12-10 |  | TL | Prayer Captain to list prayer requests on prayer wall in the WIC
55 | 2012-12-10 |  | TL | Luggage Coordinator to confirm luggage limitations and coach the team on packing
56 | 2012-12-10 |  | TT | Team Treasurer to turn in all money to MB in Mission Envelope provided at Treasurer Training
57 | 2012-12-10 |  | TL | Send housing list to field partner or confirm hotel reservation if needed
58 | 2012-12-10 |  | TL | Schedule Post Project meeting with MD
59 | 2012-12-10 |  | TL | Confirm Commissioning date with LC and have your team prepared to attend
60 | 2012-12-10 |  | LC | LC will send insurance details to TL
30 days prior to departure
61 |  |  | TL/MD | Team Training Session #5
62 |  |  | TT | 90% of per person cost is due form each team member
10-15 days prior to departure
63 | 2012-12-27 |  | TL/MD | Team Training Session #6
64 | 2012-12-27 |  | TL | Prepare field arrival orientation in conjunction with your field partner
65 | 2012-12-27 |  | TT | Contact TT to request cash advance, if necessary wire to field partner (2 weeks out)
Note: MD must review and sign cash advance request
Note: please contact your bank to discuss "bank holds" on cash advance checks
66 |  |  | TT | 100% of per person cost is due form each team member
67 | 2013-01-03 |  | TL | Have Luggage Coordinator weigh, tag, and inventory all bags | Bag Assignment List
68 | 2013-01-03 |  | TL | Assemble TL Notebook and prepare all documents for travel | Team Leader Notebook Plan
69 | 2013-01-03 |  | TL/MD | Review Project Checklist with MD
On-the-field
70 | 2013-01-10 |  | TL | Communicate with Prayer Captain to send updates back home, post prayer items on wall in WIC
71 | 2013-01-10 |  | TL | Have team members complete Team Member Debrief Forms | Team Member Debrief Form
72 | 2013-01-10 |  | TL | Complete Team Leader Debrief Form | Team Leader Debrief Form
Post-field
73 | 2013-01-24 |  | TL/MD | Team Training Session #7
74 | 2013-01-24 |  | TL | Disciple your team about sending a follow up thank you/update to their supporters
75 | 2013-01-24 |  | TL/MD | Have a post project meeting with MD to turn in debrief and complete the project | Post Project File
76 | 2013-01-24 |  | TT | Work with Team Treasurer to complete Cash Advance Reconcilliation for MB within 2 weeks of return | Cash AdvanceReconciliation Form
77 | 2013-01-24 |  | TL/MD | Reconcile Project Budget with actual project costs and turn in to MD | Budget
Note on C2: Enter departure date in format: DD/MM/YY
Note on C3: Enter return date in format: DD/MM/YY
Note on B10: This field will be automatically calculated when you enter MISSION START DATE above.
Note on B12: This field will be automatically calculated when you enter MISSION START DATE above.
Note on B13: This field will be automatically calculated when you enter MISSION START DATE above.
Note on B14: This field will be automatically calculated when you enter MISSION START DATE above.
Note on B21: This field will be automatically calculated when you enter MISSION START DATE above.
Note on B53: This field will be automatically calculated when you enter MISSION START DATE above.
Note on B66: This field will be automatically calculated when you enter MISSION START DATE above.
Note on B74: This field will be automatically calculated when you enter MISSION START DATE above.
Note on B88: This field will be automatically calculated when you enter MISSION END DATE above.
Note on B31: This field will be automatically calculated when you enter MISSION START DATE above.
Note on B32: This field will be automatically calculated when you enter MISSION START DATE above.
Note on B33: This field will be automatically calculated when you enter MISSION START DATE above.
Note on B69: This field will be automatically calculated when you enter MISSION START DATE above.
Note on B40: This field will be automatically calculated when you enter MISSION START DATE above.
Note on B8: This field will be automatically calculated when you enter MISSION START DATE above.
Note on B18: This field will be automatically calculated when you enter MISSION START DATE above.
Note on B17: This field will be automatically calculated when you enter MISSION START DATE above.
Note on B19: This field will be automatically calculated when you enter MISSION START DATE above.
Note on B20: This field will be automatically calculated when you enter MISSION START DATE above.
Note on B22: This field will be automatically calculated when you enter MISSION START DATE above.
Note on B28: This field will be automatically calculated when you enter MISSION START DATE above.
Note on B42: This field will be automatically calculated when you enter MISSION START DATE above.
Note on B43: This field will be automatically calculated when you enter MISSION START DATE above.
Note on B44: This field will be automatically calculated when you enter MISSION START DATE above.
Note on B46: This field will be automatically calculated when you enter MISSION START DATE above.
Note on B7: This field will be automatically calculated when you enter MISSION START DATE above.

## ALL
SHORT TERM MISSION PREPARATION
MISSION START DATE |  |  | 2008-04-04 | DESTINATION: |  | Click on hyperlinks
MISSION END DATE |  |  | 2008-04-11 | MISSION LEADER: |  | below to open the
RESPONSIBILITIES: MA= Mission Assistant MD= Mission Dept. Staff TL = Team Leader |  |  |  | REGION DIRECTOR: |  | listed documents.
LINE NO. | RESP | DATE DUE | DATE COMPL. | TASK DESCRIPTION | Instruc. | DOCUMENT LINKS
Tasks due 6 months before mission start
1 | TL | 2007-10-01 |  | Contact field partner to coordinate project dates; inquire about in country cost and mission opportunities for your team.
2 | TL | 2007-10-01 |  | Contact Partnership Regional Director for project assessment and approval. | 1 | Project Fact Sheet.doc
3 | TL | 2007-10-01 |  | Missions Assistant contacted to plan missions project logistics. (Project Fact Sheet, Budget Sheet) | 2, 3,5 | BUDGET Sheet.doc
4 | TL/ MA | 2007-10-01 |  | Contact Travel Coordinator (Andrea Miller) concerning tickets. Acquire ticket costs. | 4
5 | TL | 2007-10-01 |  | Pray and fast for God to bring the right team members.
6 | TL | 2007-10-01 |  | Develop mission information packet for team members. | 9 | Team Information Packet.doc
7 | TL/ MA | 2007-10-01 |  | Schedule team meetings. Contact Missions' Assistant to reserve room. | 7
8 | TL | 2007-10-01 |  | Contact potential team members (friends, Sunday School class members, church members).
Tasks due 5 months before mission start
9 | TL | 2007-11-01 |  | Submit copy of budget proposal to Missions Office.
10 | TL | 2007-11-01 |  | Find out if your country of travel requires visa to get in. Also find out passport requirements. In most cases passport needs to be valid at least for 6 months from day of travel. |  | Member List & Prep Card.xls
11 | TL | 2007-11-01 |  | Recruit team members through meetings, prayer times, and invitations to SS classes.
12 | TL | 2007-11-01 |  | Develop initial team member list. |  | Member List & Prep Card.xls
Tasks due 4 months before mission start
13 | TL | 2007-12-02 |  | Finalize team members.
14 | TL | 2007-12-02 |  | Distribute applications and missions info packets. | 16 | TeamMemberPacket.pdf
15 | TL/MD | 2007-12-02 |  | Develop prayer strategy: team prayer captain, home prayer captain, home prayer network, fasting, etc. Submit prayer form to Regional Director. | 10 | Prayer Strategy Form.doc
16 | TL | 2007-12-02 |  | Select team treasurer. Contact Missions Bookkeeper (Shirley Hughes) to complete treasurer training. | 6 | Treasurer Agreement.doc
17 | TL | 2007-12-02 |  | Write and mail support letters. Team leader shall review all letters prior to mailing. |  | Member packet pp13-16
18 | TL/MA | 2007-12-02 |  | Check to see if every team member has current passports or have applied for one. | 15 | Leader packet p 10-11
19 | TL | 2007-12-02 |  | Develop leadership team (Assistant Leader, ministry Captains). | 8
20 | TL | 2007-12-02 |  | Contact Missions Assistant to reserve airport transportation, if FBCW vans are available.
21 | TL/MD | 2007-12-02 |  | Prayer captain to commence leading team in prayer, fasting. | 10,11
22 | TL | 2007-12-02 |  | Set up team communications (phone, email, etc.) Provide copy of all communications to Missions Assistant. | 13
Tasks due 3 months before mission start
23 | TL/MA | 2008-02-02 |  | Collect completed team participation, application and medical forms, minor affidavits and submit to Missions Office. Keep copies for your file. | 20
24 | TL | 2008-01-02 |  | Contact Missions Office if net team financial support committed is less that 65% of total budget.
25 | TL | 2008-01-02 |  | Collect prayer partner list from each team member (a minimum of 10 per team member). Submit to Missions Office.
26 | TL/MA | 2008-01-02 |  | Acquire travel visa, if necessary. | 14
27 | TL/MD | 2008-01-02 |  | Hold regular team meetings for prayer, ministry preparation and discipleship.
28 | TL/MA | 2008-01-02 |  | Prepare ministry teams (music, drama, puppets, evangelism, etc.) Missions Dep. has some resources available. | 17
Tasks due 2 months before mission start
29 |  | 2008-01-02 |  | Submit copy of each passport to Missions Office. | 32
30 | TL/MD | 2008-02-02 |  | Develop field evacuation plan, if mission is to a foreign country. | 24
31 | TL/MA | 2008-02-02 |  | Verify financial support for all members. Contact Missions Office for all team members having commitments less that 50% of need. | 29
32 | TL | 2008-02-02 |  | Hold regular team meetings for prayer, ministry preparation and discipleship.
33 | TL | 2008-02-02 |  | Contact Missions Assistant if you need media equipment for your trip.
34 | TL | 2008-02-02 |  | Send thank you letters to supporters and mail second round of support letters. | 27 | Member packet pp 13-16
35 | TL | 2008-02-02 |  | Contact Travel Coordinator (Andrea Miller) to get an update on tickets.
36 | TL | 2008-02-02 |  | Contact Missions Assistant to verify transportation to and from airport. Find drivers for your team. | 26
Tasks due 1 month before mission start
37 | MS | 2008-03-04 |  | Contact Missions Assistant to request travel insurance. | 21
38 | TL/MA | 2008-03-04 |  | Contact Missions Assistant to schedule team commissioning. | 25
39 | TL | 2008-03-04 |  | 2nd meeting with Missions Director or Missions Assistant to go over checklist. | 24
40 | TL | 2008-03-04 |  | Communicate to Missions Director any extra curriculum activities while on the field (What is the team going to do during free time?).
41 | TL/MA | 2008-03-04 |  | If taking any sound / media equipment. Complete media / sound equipment list for customs (type, serial number, cost, weight) and submit to missions office. | 22
42 | TL/MA | 2008-03-04 |  | Complete team covenant. Have team sign; and submit copy to Missions Office. | 28 | Team Covenant.doc
43 | TL | 2008-03-04 |  | Collect final team funds. | 30
44 | TL | 2008-03-04 |  | Schedule post mission debrief meeting. | 31
45 | TL | 2008-03-04 |  | Send housing list to field director. | 38
Tasks due 2 weeks before missions start
46 | TL/MA | 2008-03-21 |  | Acquire tickets from Travel Coordinator (Andrea Miller). Match tickets to passport names (first and last names must match exactly). | 35
47 | TL/MA | 2008-03-21 |  | Make sure you have copies of all tickets. | 35
48 | MS | 2008-03-21 |  | Contact Missions Assistant to request cash advance. If necessary wire to field partner. | 36 | Leader packet p18
49 | TL/MA | 2008-03-21 |  | Confirm luggage limitations and inform team. | 42
50 | TL | 2008-03-21 |  | Review dress code and packing list. | 39
51 | TL | 2008-03-21 |  | Procure first aid kit from Missions Office. | 40
52 | TL | 2008-03-21 |  | Prepare field arrival orientation. | 46
53 | Team | 2008-03-21 |  | Purchase missionary gifts, if appropriate. | 47 | Member packet p 20
54 | TL | 2008-03-21 |  | Brief team on airport check-in/immigration procedures. | 43 | Leader packet pp 34-35
Tasks due 1 week before mission start
55 | TL | 2008-03-28 |  | Begin packing team supplies and equipment. |  | Member packet p 20
56 | TL/MD | 2008-03-28 |  | Verify checklist items. | 44,45,46
57 | TL | 2008-03-28 |  | Conduct final team meetings and prayer time. | 48
Tasks due 3 days before mission start
58 | TL/MA | 2008-04-01 |  | Complete team leader travel file. Use Short Term Team Leader notebook plan. | 51 | Leader packet pp 36-38
59 | TL | 2008-04-01 |  | Review checklist with regional director and assistant. | 52
60 | TL | 2008-04-01 |  | Weigh all team equipment and assign team equipment to individual team members for transport to airport and check-in. Label each ministry bag. Ensure no violation of airline limitations. | 49
Tasks due while on the mission field
61 | TL | DAILY |  | Record daily entries in activity log.
62 | TL | 2008-04-11 |  | Complete field debrief and collect team member debrief forms.
63 | TL | 2008-04-11 |  | Write thank you letter to supporters. |  | member packet p 17
Tasks due 2 weeks after mission end
64 | TL | 2008-04-25 |  | Reconcile team advance/expenses & submit to Mission Assistant. | 56 | Cash Reconciliation Form.doc
65 | TL | 2008-04-25 |  | Complete Team Leader debrief form. Submit to Missions Assistant. | 57 | Leader packet p 37
66 | TL | 2008-04-25 |  | Submit team member debrief forms to mission assistant. | 58
67 | TL/MA | 2008-04-25 |  | Assign team members to debrief Sunday school classes.
68 | TL | 2008-04-25 |  | Post missions project team debrief.
69 | TL/MD | 2008-04-25 |  | Meet with regional director for leader debrief. | 59
Note on F8: Regional Director contacted/trip approval finalized. Regional Director will assist the team leader in making sure that each trip meets church guidelines and has departmental approval.
Note on F9: Missions Assistant contacted/planning meeting scheduled - to discuss the logistics of the project. Team leader action list reviewed with Missions Assistant – The Missions Assistant will review this sheet in your packet with the team leader at the planning meeting. Budget prepared with field/network partners. Budget proposal completed. The team leader will fill out the budget proposal sheet with the Missions Assistant 4-6 months before the date of departure. At this time the team leader should have talked with field personnel about in-country costs. Field Personnel Contact – They will assist the team leader in developing a budget for the team while on the field. An approximate cost is needed per team member, per day. See appendix.
Note on F10: Cost of the tickets acquired from Missions Assistant. – Mission’s assistant will book all tickets unless approved otherwise.
Note on F12: Team Information Packet developed (required for teams of 5 or more). See disk for example on TIP.
Note on F13: Team meetings set with room reservations: ALL upcoming team meetings are to be scheduled 4 months before the departure date with the Missions Assistant
Note on D2: Enter departure date in format: DD/MM/YY
Note on D3: Enter return date in format: DD/MM/YY
Note on F29: Field prayer captain chosen, list of team members developed with on-going prayer needs list in preparation for the project. – This very important position is someone on the field who is included as a team member that will prioritize and coordinate team prayer efforts from the field to the team preparing to go. Prayer captain chosen and prayer lists of team members and requests given to the church family (e-mail: list of 10 people who will pray each day for the team). This team member will prioritize and coordinate team prayer in preparation for the project praying for team, support, field personnel, project, evangelism efforts, weather, health, families, etc.
Note on F30: Team communication system set up (copy all communications with team to Regional Director's Assistant). Set up communication network (e-mail, phone, other) and copy all communications with Missions Assistant.
Note on F37: Ministry teams prepared (music, drama, puppets, evangelism, etc.) – If the team will be doing ministry performances they must be prepared in a quality manner. GUIDE: If it is not good enough for our church family, it is not good enough! ALSO: If ministry programs and/or materials are being translated, please check with nationals to be sure!
Note on C8: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C9: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C10: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C11: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C12: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C13: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C14: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C18: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C19: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C28: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C29: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C30: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C36: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C37: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C40: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C44: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C46: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C48: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C49: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C52: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C53: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C54: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C55: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C56: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C58: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C59: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C60: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C61: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C62: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C63: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C64: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C65: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C66: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C68: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C69: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C70: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C74: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C77: This field will be automatically calculated when you enter MISSION END DATE above.
Note on C78: This field will be automatically calculated when you enter MISSION END DATE above.
Note on C80: This field will be automatically calculated when you enter MISSION END DATE above.
Note on C81: This field will be automatically calculated when you enter MISSION END DATE above.
Note on C82: This field will be automatically calculated when you enter MISSION END DATE above.
Note on C83: This field will be automatically calculated when you enter MISSION END DATE above.
Note on C84: This field will be automatically calculated when you enter MISSION END DATE above.
Note on C85: This field will be automatically calculated when you enter MISSION END DATE above.
Note on F40: Verified field plan for emergency evacuation for team and/or individual. This plan must be communicated to the Regional Director and assistant before the team’s departure!
Note on F44: Thank you letters written for individual and team support. The question is “Why would someone not do this?”
Note on F46: Transportation to/from the airport finalized. The team leader is to contact the Mission Assistant to arrange transportation for the team. She will see that all transportation needed is provided.
Note on F48: Travel insurance requested: One month before departure, the team leader is to submit a roster of team members to the Missions Assistant who will submit an application for insurance to the insurance company. Two sources: Adams & Associates www.aaintl.com or Brotherhood Mutual www.brotherhoodmutual.com
Note on F49: Team commissioning scheduled: Our Pastor, Johnny Hunt will commission all teams to the field. The Missions Assistant will schedule this date and give it to the team leader. IT IS VERY IMPORTANT THAT ALL TEAM MEMBERS BE PRESENT WHEN THE TEAM NAMES ARE ANNOUNCED.
Note on F52: Sound equipment list with type, serial number, approximate cost, and weigh prepared for customs. Send itemized list to the field director. List can be obtained from the Media department.
Note on F53: Team covenant completed: Each team is required to issue a covenant based on the Word of God. It will address the focus of the trip; relationships between team members, field personnel, and internationals; responsibilities of each team member; activities; safety, etc. This is to be turned in no later than 2 months before departure to the Missions Assistant. See appendix.
Note on F54: Final payment of team funds. No later than one month before departure, the balance of budgeted team funds should be turned in to the Missions Office Bookkeeper. Any money received after this deadline is to be turned as well to the bookkeeper and will be credited to the team's account. Please make every effort to have money in one month before departure for logistical reasons.
Note on F55: Schedule debrief meeting before the team leaves the field. This meeting needs to be scheduled to take place on the field if possible. The field personnel of the country to be visited may need to be contacted to set this meeting.
Note on F58: Copies of tickets made and filed for trip. Ticket numbers are needed for any lost, stolen, or damaged tickets.
Note on F56: Housing list sent to field director as needed. For field partners preparation for homes, hotels, dorms, etc.
Note on F59: Copies of tickets made and filed for trip. Ticket numbers are needed for any lost, stolen, or damaged tickets.
Note on F60: Cash advance received/wired to field partner. The cash advance form provided in this packet is to be used to request money for in-country costs for the team, one week before departure. The team leader should schedule a time to fill this form out and verify that the funds in the account will cover the needed expenses. It should be turned into the Missions Assistant on Monday morning, and can be picked up the following Thursday AFTER 2:00 PM.
Note on F61: Check the current luggage guidelines for your carriers. Remember to check multiple carriers on your itinerary. These requirements are subject to change by the carrier at any time and can be different according to the season.
Note on F62: Review dress code and packing list. – Some cultures and ministries require different dress codes for certain events. Not having the appropriate attire with you is not an excuse. In addition, using the checklist will prevent the norm of most people over packing.
Note on F63: First aid kit picked up for packing. Pick up from the missions office or purchase and turn in receipt for reimbursement.
Note on F64: Field orientation prepared for arrival. Prepare information for orientation after arrival on the field. Introduction of field partners, team guidelines, location of security box (team tickets, passports, etc.) housing, food, ministry schedule, culture expectations, etc.
Note on F65: Missionary gifts collected or checked off for individuals to pack. Assign someone to collect and/or check off that any items needed and/or requested from the field. If at all possible pack in personal team luggage.
Note on F66: Airport briefing completed on check-in. Please walk through airport check-in, luggage issues, and security questions, and the importance of always being kind. If problems arise we certainly can be firm, but always kind! When traveling with teenagers and/or first time travelers this is very important. OUR TESTIMONY BEGINS HERE!
Note on F69: Make sure you have all minor affidavit forms completed and signed. You must have each minor complete and have signed by his or her legal guardian or parent even if the parent is accompanying the minor on the trip. Preparation for immigration and customs procedures covered (remember how to answer security questions.) – See detailed explanation in appendix. Field orientation prepared for arrival. Prepare information for orientation after arrival on the field. Introduction of field partners, team guidelines, location of security box (team tickets, passports, etc.) housing, food, ministry schedule, culture expectations, etc.
Note on F70: Final leadership meeting for prayer. Meet with travel team, support group, parents, spouses etc. for corporate prayer.
Note on F74: Team equipment securely packed, weighed, and assigned to an individual for airport check-in. Luggage requirements meet (weight, size, number.) Logistic coordinator and/or team leader check that all team equipment has been weighed and meets airline specifications to avoid fines and the possibility that items will be disapproved for travel.
Note on F80: Team expense/advance reconciliation turned in to Missions department (10 days or less after team returns.) One week after the trip, the team expense report with all receipts, journals and any cash left over are to be turned in to Shirley Hughes. The team treasurer training, mentioned above, will cover the correct method of logging team expenses. See disk for form.
Note on F81: Team leader review the “After Action Review” sheet & topics. See team leader manual. Set up meeting ASAP after the completion of the project and all paperwork is prepared.
Note on F82: Team evaluation forms collected & compiled. Team leader compile these for the after-action review.
Note on F85: Team leader debrief with Regional Area Director. This will be a MANDATORY one-half to one-hour appointment with the Area Director no later than 2 weeks after return.
Note on C22: This field will be automatically calculated when you enter MISSION START DATE above.
Note on F22: Team Member Manuals and Information Packets distributed: Each team member MUST have a manual, but please only distribute manuals to those committed to the trip. Information Packets may be obtained from the Missions Assistant PLEASE NOTE: Information Packets are to be requested at least one week in advance. Complete information packets ASAP. Copy to Missions Assistant and insert an original into the team notebook.
Note on C23: This field will be automatically calculated when you enter MISSION START DATE above.
Note on F23: Field prayer captain chosen, list of team members developed with on-going prayer needs list in preparation for the project. – This very important position is someone on the field who is included as a team member that will prioritize and coordinate team prayer efforts from the field to the team preparing to go.
Note on C21: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C24: This field will be automatically calculated when you enter MISSION START DATE above.
Note on F24: Team treasurer selected and trained: This is a required position. Please prayerfully consider who the team treasurer will be. This person will handle ALL the team funds including the money taken to the field. After choosing the team treasurer - a training session is to be scheduled with Shirley Hughes, (678-494-2722, shirley.hughes@fbcw.net). This is MANDATORY.
Note on C33: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C34: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C27: This field will be automatically calculated when you enter MISSION START DATE above.
Note on F27: Leadership team developed. Assistant, prayer captain, evangelism, logistics, etc. as needed especially for teams with 20 or more members. This leadership development principal will involve more people personally.
Note on C42: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C43: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C41: This field will be automatically calculated when you enter MISSION START DATE above.
Note on F41: Final budget adjustments completed. If any change takes place due to loss of team members and a readjustment is needed.
Note on C50: This field will be automatically calculated when you enter MISSION START DATE above.
Note on F50: Verified field plan for emergency evacuation for team and/or individual. This plan must be communicated to the Regional Director and assistant before the team’s departure!
Note on C51: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C72: This field will be automatically calculated when you enter MISSION START DATE above.
Note on F72: Team leader travel file complete. The team leader file checklist is in the appendix.
Note on C73: This field will be automatically calculated when you enter MISSION START DATE above.
Note on F73: Meeting with Regional Director and assistant to review checklist. –Set this meeting at least 21-28 days prior to team departure to pray and review checklist with Regional Director and assistant.
Note on C35: This field will be automatically calculated when you enter MISSION START DATE above.
Note on F35: Visa information acquired: Some countries require visas to be paid for in advance. All visa applications and information may be obtained from the Missions Assistant.
Note on C26: This field will be automatically calculated when you enter MISSION START DATE above.
Note on F26: Passport information acquired: Passports are required for all international travel. Passports applications may be obtained at the Sprayberry Post Office on Sandy Plains Road in Marietta. An original birth certificate is needed for the application and acquisition of a passport. Passport and visa photos are also made at this post office. Passport fees are the responsibility of each individual team member. Passports need to be applied for (4) months before departure. In emergencies, a passport can be acquired in about two weeks but does carry a heavy penalty fee. PLEASE NOTE: Passport and visa photos can be made for a small charge through the FBCW Publication department if an appointment is scheduled for the entire team.
Note on C7: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C17: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C16: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C32: This field will be automatically calculated when you enter MISSION START DATE above.
Note on F32: Participation, application and medical forms collected. 2-4 months before departure, all medical forms, testimonies, waiver agreements, personal references, etc., are to be filled out and turned into the team leader and then, submitted to the Missions Assistant. New forms are to be filled out for each trip. The team leader is to turn in ALL team member's forms at one time in a file folder, please, after reviewing each applicant’s information. Potential problems need to be addressed with the Area Director at this point.
Note on C25: This field will be automatically calculated when you enter MISSION START DATE above.
Note on C39: This field will be automatically calculated when you enter MISSION START DATE above.
Note on F39: Passports checked and turned in (or checked off) with a copy. Check the signature. 2 weeks before departure, the team leader is to collect ALL the team member’s passports and verify that the team members have signed them all. The team leader is to make (4) copies of each passport. One copy of each passport should be given to the following: The Missions Assistant, the team leader, a team member's family member or personal contact at home, and one copy is to remain on the team member’s person at ALL times.

## Ldr tasks only
This sheet TBD

## Instructions
Short-term Mission Preparation Check List Instructions
1. Regional Director contacted/trip approval finalized. Regional Director will assist the team leader in making sure that each trip meets church guidelines and has departmental approval.
2. Missions Assistant contacted/planning meeting scheduled - to discuss the logistics of the project.
3. Team leader action list reviewed with Missions Assistant – The Missions Assistant will review this sheet in your packet with the team leader at the planning meeting.
4. Cost of the tickets acquired from Missions Assistant. – Mission’s assistant will book all tickets unless approved otherwise.
5. Budget prepared with field/network partners. Budget proposal completed. The team leader will fill out the budget proposal sheet with the Missions Assistant 4-6 months before the date of departure. At this time the team leader should have talked with field personnel about in-country costs. Field Personnel Contact – They will assist the team leader in developing a budget for the team while on the field. An approximate cost is needed per team member, per day. See appendix.
6. Team treasurer selected and trained: This is a required position. Please PRAYERFULLY consider who the team treasurer will be. This person will handle ALL the team funds including the money taken to the field. After choosing the team treasurer - a training session is to be scheduled with Shirley Hughes, (678-494-2722, shirley.hughes@fbcw.net). This is MANDATORY.
7. Team meetings set with room reservations: ALL upcoming team meetings are to be scheduled 4 months before the departure date with the Missions Assistant
8. Leadership team developed. Assistant, prayer captain, evangelism, logistics, etc. as needed especially for teams with 20 or more members. This leadership development principal will involve more people personally.
9. Team Information Packet developed (required for teams of 5 or more). See appendix for example on TIP.
10. Field prayer captain chosen, list of team members developed with on-going prayer needs list in preparation for the project. – This very important position is someone on the field who is included as a team member that will prioritize and coordinate team prayer efforts from the field to the team preparing to go.
11. Prayer captain chosen and prayer lists of team members and requests given to the church family (e-mail: list of 10 people who will pray each day for the team). This team member will prioritize and coordinate team prayer in preparation for the project praying for team, support, field personnel, project, evangelism efforts, weather, health, families, etc.
12. Home prayer-captain chosen and e-mail list developed for on-the-field needs during the project. This team member will not travel to the field but will coordinate prayer requests with the prayer captain during the project as much as possible and will relay needs to the home support group and mission office.
13. Team communication system set up (copy all communications with team to Regional Director's Assistant). Set up communication network (e-mail, phone, other) and copy all communications with Missions Assistant.
14. Visa information acquired: Some countries require visas to be paid for in advance. All visa applications and information may be obtained from the Missions Assistant.
15. Passport information acquired: Passports are required for all international travel. Passports applications may be obtained at the Sprayberry Post Office on Sandy Plains Road in Marietta. An original birth certificate is needed for the application and acquisition of a passport. Passport and visa photos are also made at this post office. Passport fees are the responsibility of each individual team member. Passports need to be applied for (4) months before departure. In emergencies, a passport can be acquired in about two weeks but does carry a heavy penalty fee. PLEASE NOTE: Passport and visa photos can be made for a small charge through the FBCW Publication department if an appointment is scheduled for the entire team.
16. Team Member Manuals and Information Packets distributed: Each team member MUST have a manual, but please only distribute manuals to those committed to the trip. Information Packets may be obtained from the Missions Assistant PLEASE NOTE: Information Packets are to be requested at least one week in advance. Complete information packets ASAP. Copy to Missions Assistant and insert an original into the team notebook.
17. Ministry teams prepared (music, drama, puppets, evangelism, etc.) – If the team will be doing ministry performances they must be prepared in a quality manner. GUIDE: If it is not good enough for our church family, it is not good enough! ALSO: If ministry programs and/or materials are being translated, please check with nationals to be sure!
18. Media team notified of sound equipment needs (contact Missions Assistant.) – In order to use the Mission department sound system, the media department must have ample notification and a qualified person to operate and care for the equipment will need to be on the team.
19. Dates verified with ticket list (any changes made at this time.) Team leader has final responsibility to verify tickets one week before departure.
20. Participation, application and medical forms collected. 2-4 months before departure, all medical forms, testimonies, waiver agreements, personal references, etc., are to be filled out and turned into the team leader and then, submitted to the Missions Assistant. New forms are to be filled out for each trip. The team leader is to turn in ALL team member's forms at one time in a file folder, please, after reviewing each applicant’s information. Potential problems need to be addressed with the Area Director at this point.
21. Travel insurance requested: One month before departure, the team leader is to submit a roster of team members to the Missions Assistant who will submit an application for insurance to the insurance company. Two sources: Adams & Associates www.aaintl.com or Brotherhood Mutual www.brotherhoodmutual.com
22. Sound equipment list with type, serial number, approximate cost, and weigh prepared for customs. Send itemized list to the field director. List can be obtained from the Media department.
23. Emergency contact numbers for field location supplied to Missions office. There must be emergency numbers on file with the Regional Director and assistant. Any change in these numbers on the field must be communicated ASAP on arrival.
24. Verified field plan for emergency evacuation for team and/or individual. This plan must be communicated to the Regional Director and assistant before the team’s departure!
25. Team commissioning scheduled: Our Pastor, Johnny Hunt will commission all teams to the field. The Missions Assistant will schedule this date and give it to the team leader. IT IS VERY IMPORTANT THAT ALL TEAM MEMBERS BE PRESENT WHEN THE TEAM NAMES ARE ANNOUNCED.
26. Transportation to/from the airport finalized. The team leader is to contact the Mission Assistant to arrange transportation for the team. She will see that all transportation needed is provided.
27. Thank you letters written for individual and team support. The question is “Why would someone not do this?”
A practical suggestion for team leaders is to collect thank you letters pre-stamped with addresses when receiving support checks to turn in to the team treasure. This is a good accountability system for all.
28. Team covenant completed: Each team is required to issue a covenant based on the Word of God. It will address the focus of the trip; relationships between team members, field personnel, and internationals; responsibilities of each team member; activities; safety, etc. This is to be turned in no later than 2 months before departure to the Missions Assistant. See appendix.
29. Final budget adjustments completed. If any change takes place due to loss of team members and a readjustment is needed.
30. Final payment of team funds. No later than one month before departure, the balance of budgeted team funds should be turned in to the Missions Office Bookkeeper. Any money received after this deadline is to be turned as well to the bookkeeper and will be credited to the team's account. Please make every effort to have money in one month before departure for logistical reasons.
31. Schedule debrief meeting before the team leaves the field. This meeting needs to be scheduled to take place on the field if possible. The field personnel of the country to be visited may need to be contacted to set this meeting.
32. Passports checked and turned in (or checked off) with a copy. Check the signature. 2 weeks before departure, the team leader is to collect ALL the team member’s passports and verify that the team members have signed them all. The team leader is to make (4) copies of each passport. One copy of each passport should be given to the following: The Missions Assistant, the team leader, a team member's family member or personal contact at home, and one copy is to remain on the team member’s person at ALL times.
33. Three copies of entire team list with passport numbers beside names made - for distribution to field leaders, some international bus company requirements, etc.
34. Tickets received and names verified with passport (first & last). The Missions Assistant will contact the team leader and notify them to pick up the airplane tickets. Please verify that each ticket is correct.
35. Copies of tickets made and filed for trip. Ticket numbers are needed for any lost, stolen, or damaged tickets.
36. Cash advance received/wired to field partner. The cash advance form provided in this packet is to be used to request money for in-country costs for the team, one week before departure. The team leader should schedule a time to fill this form out and verify that the funds in the account will cover the needed expenses. It should be turned into the Missions Assistant on Monday morning, and can be picked up the following Thursday AFTER 2:00 PM.
37. Additional team funds (if needed) advance requested for travel. Financial office procedures require requests to be in on Monday for checks to be received by Thursday of the same week.
38. Housing list sent to field director as needed. For field partners preparation for homes, hotels, dorms, etc.
39. Review dress code and packing list. – Some cultures and ministries require different dress codes for certain events. Not having the appropriate attire with you is not an excuse. In addition, using the checklist will prevent the norm of most people over packing.
40. First aid kit picked up for packing. Pick up from the missions office or purchase and turn in receipt for reimbursement.
41. Travel agency number filed for emergency at airport. Have this number with you for any difficulties at the airport. Our travel agents are very helpful in working with the airlines when problems arise. Your Ministry Assistant can help you during church office hours. ALSO: keep the home and cell numbers of the Regional Directors with you as well.
42. Check the current luggage guidelines for your carriers. Remember to check multiple carriers on your itinerary. These requirements are subject to change by the carrier at any time and can be different according to the season.
43. Airport briefing completed on check-in. Please walk through airport check-in, luggage issues, and security questions, and the importance of always being kind. If problems arise we certainly can be firm, but always kind! When traveling with teenagers and/or first time travelers this is very important. OUR TESTIMONY BEGINS HERE!
44. Make sure you have all minor affidavit forms completed and signed. You must have each minor complete and have signed by his or her legal guardian or parent even if the parent is accompanying the minor on the trip.
45. Preparation for immigration and customs procedures covered (remember how to answer security questions.) – See detailed explanation in appendix.
46. Field orientation prepared for arrival. Prepare information for orientation after arrival on the field. Introduction of field partners, team guidelines, location of security box (team tickets, passports, etc.) housing, food, ministry schedule, culture expectations, etc.
47. Missionary gifts collected or checked off for individuals to pack. Assign someone to collect and/or check off that any items needed and/or requested from the field. If at all possible pack in personal team luggage.
48. Final leadership meeting for prayer. Meet with travel team, support group, parents, spouses etc. for corporate prayer.
49. Team equipment securely packed, weighed, and assigned to an individual for airport check-in. Luggage requirements meet (weight, size, number.) Logistic coordinator and/or team leader check that all team equipment has been weighed and meets airline specifications to avoid fines and the possibility that items will be disapproved for travel.
50. Equipment list prepared with identification of each ministry team bag. Have a master list of all team-checked bags with numbers assignment, weight and description listed in case anything is missing on arrival.
51. Team leader travel file complete. The team leader file checklist is in the appendix.
52. Meeting with Regional Director and assistant to review checklist. –Set this meeting at least 21-28 days prior to team departure to pray and review checklist with Regional Director and assistant.
53. Team meetings completed. Completion of all preparation and planning meetings before departure.
54. Departure guidelines completed – Review departure guidelines. See appendix for list.
55. Field debriefs completed and evaluation forms returned. See evaluation form in appendix.
56. Team expense/advance reconciliation turned in to Missions department (10 days or less after team returns.) One week after the trip, the team expense report with all receipts, journals and any cash left over are to be turned in to Shirley Hughes. The team treasurer training, mentioned above, will cover the correct method of logging team expenses. See appendix.
57. Team leader review the “After Action Review” sheet & topics. See team leader manual. Set up meeting ASAP after the completion of the project and all paperwork is prepared.
58. Team evaluation forms collected & compiled. Team leader compile these for the after-action review.
59. Team leader debrief with Regional Area Director. This will be a MANDATORY one-half to one-hour appointment with the Area Director no later than 2 weeks after return.
60. Team summary report for FBCW website completed. (Acts 14:27 model). All the reports will not be able to be presented, but please have available pictures and script for editing in a 15-20 second format if you want the project to be considered.